## Habitat Sub-processes
# | Sub-process | Goal | Step # | Description | Step "owner" | Timeline | Comments | Database project implications | Actions
A | Identify worthy projects | Top notch candidate projects that number more than we can handle | 1 | Project candidates are nominated through: (1) landowner self-identifcation thru website; (2) Proposed by volunteer; (3) Proposed by partner organization; (4) Other | Various(?) |  | All potential projects should be placed in website form | Yes | Simplify on-line form to that which the landowner is likely to know;
|  |  | 2 | HRP conducts initial remote review and discusses with landowner; Evaluates project with recommendation to Habitat Committee | HRP |  | Use evaluation form; Landowners are informed unsuitable projects and reasons | Yes
|  |  | 3 | Habitat Committee reveiws project and determines go/no-go, dollar limit; Approved projects are added to HRP project list | Habitat Committee Chair |  | Includes cost estimate, source of funds, and estimated milestone timeline | Yes | Review Project form to ensure needed info is on it. Database project
B | Undertake and complete a project | Efficiently managed projects that stand the test of time | 1 | Milestone 1: Project Approved by Habitat Committee | Habitat Committee Chair |  | Includes cost estimate, source of funds, and estimated milestone timeline | Yes | Are these the right milestones? May be influenced by when we can submit for reimbursement under the various grants
|  |  | 2 | Milestone 2: HRP develops landowner-approved designs | HRP |  | Update costs on project spreadsheet / database | Yes | There be an individual project sheet that tracks progress on a given project: allows for individual status review and roll up into grant report, monthly project report, etc Database project
|  |  | 3 | Milestone 3: Permits developed by HRP and submitted | HRP |  | Update costs on project spreadsheet / database | Yes
|  |  | 4 | Milestone 4: Contractors work complete | HRP |  | Update costs on project spreadsheet / database
|  |  | 5 | Milestone 5: Project complete | HRP |  | WWA paperwork provided to landowner; Landowner contact information incorporated in WWA database; Before and after story completed; Update costs on project spreadsheet / database | Yes | Review completion paperwork to landowner, should include WWA membership information, as well as maintenance responsinilities and easement agreement
C | Invoicing and payment | Accurate, rapid contractor payment and reimbursement from grants | 1 | Identify grant's threshholds for payment for each grant type (i.e., milestones, project completion, as expense is incurred…) | AD | upon receipt of grant approval | Need to define payment threshholds - connect to Milestones above in sub-process B? | No | revisit invoice format
|  |  | 2 | Establish grant worksheet to track progress against requirements and draws upon funding | AD | upon receipt of grant approval | To include results progress, such as acreage | No | same as D4 below
|  |  | 3 | Submit monthly (1) invoice to AD and prospect/project progress report to Hab Committee / ED | HRP | Monthly |  | Maybe | Reconfigure current invoice to reflect projects, hours/expenses and to which funding source they should be charged, remaining anticipated expenses (?)
|  |  | 4 | Reconcile monthly invoicing into grants worksheet | AD | Monthly |  | Maybe | ?? Submit to board as part of monthly financials??
|  |  | 5 | Disburse funds to contractors; Seek grant reimbursement ASAP, consistent with threshholds for payment established in C1 above | AD |  |  |  | COI prior to contractor payments
D | Manage grants | Complete, efficient and timely application, administration and reporting | 1 | Grant opportunity is identified and application is compiled | ED/HRP |  |  |  | Need to look beyond traditional sources
|  |  | 2 | Grant application approved by (or presented to) Habitat committee | HRP
|  |  | 3 | Granting authority approves grant | Approving authority
|  |  | 4 | File approved application and establish grant worksheet to track progress against requirements and draws upon funding | AD | upon receipt of grant approval | To include results progress, such as acreage |  | Need to review the current spreadsheet for project progress against grant goals
|  |  | 5 | Reconcile monthly invoicing into grants worksheet | AD | Monthly |  |  | ?? Part of monthly financials??
|  |  | 6 | Trigger grant status review at 50% and 75% funds disbursed | AD | as 50% and 75% threshholds are crossed | Intent is to routinely review grant progress and closeout requirements
|  |  | 7 | Compile/Complete/submit closeout report | HRP | As 100% funds disbursed | Links to sub-process B ("Tell the WWA project story") |  | Should include "picture stories"
|  |  | 8 | File report accepted by grantor | AD | Upon grant report approval
E | Tell the WWA project story | Timely, evocative and inspirational updates and project stories | 1 | Capture initial state of the project with both written and visual data and associate with the specific project file | HRP |  | Incoporate written description and ground photos, and if possible, aerial photos (drone or satellite) | Yes
|  |  | 2 | As work progresses and update project file with data and visual images | HRP |  | Incoporate written description and ground photos, and if possible, aerial photos (drone or satellite) | Yes
|  |  | 3 | Compile complete before/after story for newsletter | HRP |  | Incoporate written description and ground photos, and if possible, aerial photos (drone or satellite) | Yes | Incoporate into grant reporting, D7 above
|  |  | 4 | Update project map | HRP | Quarterly |  | ?
|  |  | 5 | Post updated project map | AD | Quarterly |  | No

## Invoice sample
HRP INVOICE |  | DATE: | 2022-06-01 |  | Hourly Billable rate |  | 85
Project Activity | Acres |  | Milestone | Charges against projects this month* | HRP Hours |  |  |  | Permit Fees |  |  |  | Supplies |  |  |  | Contractor Expenses |  |  |  | Comments
| Wetland | Upland |  |  | WWA* | Duck 21-22 (wild rice) | Duck 21-22 | <<Other>> | WWA | Duck 21-22 (wild rice) | Duck 21-22 | <<Other>> | WWA | Duck 21-22 (wild rice) | Duck 21-22 | <<Other>> | WWA | Duck 21-22 (wild rice) | Duck 21-22 | <<Other>>
kalbus | 10 | 2 | 3 - Permits submitted | 2366.84 | 0 | 0 | 3 |  | 0 |  | 235 |  | 0 |  | 1876.84 |  | 0 | 0 | 0 | 0 | WCS from Agri Drain, erosion permit fee
White River | 9 | 10 | 3 - Permits submitted | 0 | 7 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Ashwalde | 5 | 1 | 3 - Permits submitted | 0 | 2 |  | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Project Reviews |  |  |  | 0 | 28 |  | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Oak Ridge WPA | 26 |  | 5 - Project completed | 0 | 1 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
0
0
0
NON-Project Expenses (describe below) |  |  |  |  | 41
TOTAL | 50 | 13 |  | 2366.84 | 79 | 0 | 3 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 1876.84 | 0 | 0 | 0 | 0 | 0
* Note: HRP hours against WWA are for information, not billing purposes.
Describe non-project expenses:
staff, committee mtg, JV mtg, admin- e-mails phone conversations on projects/WWA, PR funding MOU conversations, GIS program, wetland edu class
HRP invoice | WWA |  | Duck 21-22 (wild rice) |  | Duck 21-22 |  | <<Other>> |  | TOTAL
HRP hours | n/a |  | 0 |  | 255 |  | 0 |  | 255
Permits | 0 |  | 0 |  | 235 |  | 0 |  | 235
Supplies | 0 |  | 0 |  | 1876.84 |  | 0 |  | 1876.84
Contractor | 0 |  | 0 |  | 0 |  | 0 |  | 0
Retainer | 2600 |  | n/a |  | n/a |  | n/a |  | 2600
TOTAL | 2600 |  | 0 |  | 2366.84 |  | 0 |  | 4966.84
Fund sources expensed in this invoice
| Original funding amount |  | Amount remaining from last month |  | Invoiced this month |  | Remaining funds, end of month
WWA | 0 |  | 0 |  | 2600
Duck 21-22 (wild rice) | 10000 |  | 10000
Duck 21-22 | 50000 |  | 48637.5 |  | 2366.84 |  | 46270.66
<<Other>> | 0 |  | 0 |  | 0 |  | 0
TOTAL | 60000 |  | 58637.5 |  | 4966.84 |  | 46270.66
Pull down list
Milestone / Threshhold
1 - Project approved
2 - Design completed
3 - Permits submitted
4 - Construction done
5 - Project completed