Increasing Waterfowl Hunters in Wisconsin

Wis Dept Nat Res – R3 Grant

This WWA initiative aligns with the overall mission of WWA with some connection to all 3 areas of focus (habitat, education and advocacy).  It financially benefits WWA in that work already being done can be charged to the grant and reduce stress on other funding sources.  Through the social media effort it also has the potential to attract additional WWA sponsors and members.

OBJECTIVES

Design, prototype, document and evaluate a program to attract individuals from underrepresented communities to the 2023 Waterfowl Hunters Expo

The primary target group is new (never purchased a waterfowl stamp) and novice (purchases their 1st waterfowl stamp in 2020 or after) from under-represented communities (women and people of color)

In 2023 Recruit 10 (15 additional in 2024)  new waterfowl hunters from underrepresented communities and pair with mentors for 2 mentored hunts

Attract at least 100 novice waterfowlers to the 2023 and 2024 Waterfowl Hunters Expo

Create mentored hunting opportunity for 15 novice hunters in 2023 and 2024

PLAN

(2023 timeline and plan would be used with needed adjustments to meet 2024 objectives)

Hire or contract with an individual to oversee and manage WWA R3 Grant – Nov/Dec 2022

Develop a package to market this WWA initiative to potential donors and sponsors for additional financial support or equipment donations – Dec 2022

Create expectation and contract with  marketing or social media vendor – Dec 2022

Create expectation and contract with program evaluator vendor – Jan 2023

Create a work group including individuals from under-represented communities who are waterfowl hunters (or not) to assist and provide feedback on the overall approach.  WWA currently have a partial list of individuals to be invited to the work group – Dec 2022

Utilize social media (vendor and WWA) to create awareness of this WWA initiative as a way to attract interested individuals and mentors.  The key will be to ensure the social media efforts are focus on underrepresented communities. – Jan – May 2023

Contact  and connect with “influencers” from within the target group who are currently waterfowl hunters to help in creating awareness of the WWA efforts and as a way to attract interested individuals and mentors – Jan-May 2023

Use WWA communications to attract 15-20 individuals who are interested and qualified to be waterfowl mentors – Jan-May 2023

Work with Expo Program Committee and WWA Education Committee to develop programing topics for novice and new waterfowl hunters – April/May 2023

Develop a cohort(s) of individuals (10-20) from target group who are interested in being introduced to waterfowl hunting.  Within each cohort identify a cohort leader – May-June 2023

Via zoom meetings and other venues have interactions with the cohort(s) and mentors on waterfowl related topics including participation in the 2023 Waterfowl Hunters Expo – July-Aug 2023

After 2023 WHE continue communications and connection with cohort and assigned mentors to schedule 2 mentored waterfowl hunting opportunities.

BUDGET (attached)

Total $75,206

Grant $56,405

WWA Match $$18,801

Cash Match $650

In-Kind/Donations $18,151

WWA Match

Tracking of volunteer time (mentors, Expo presenters, Expo planning)

Donation or Sponsors related to grant objectives

Grant Funding – Social Media contract and messaging

Grant Funding – Evaluation development

Grant Funding – Administration and financial accounting – Ross and Boettcher time on Expo items related to grant

Grant Funding – Program management, report writing, newsletter topics, lesson plan development – New hire, Ross and Boettcher time

Grant Funding – Expo costs related to R3 Grant efforts

Grant Funding – Expo travel costs – cohort students, mentors and staff

Grant Funding – Equipment purchases for cohort students

REQUIRED REPORTS

Interim Performance Report – Due 08/31/23

Interim Performance Report – Due 08/31/2024

Final Performance Report – Due 11/30/2024