WISCONSIN WATERFOWL ASSOCIATION

HABITAT          EDUCATION          LEGISLATION

16 October 2024

Fred Wurster

US Fish and Wildlife Service

5275 Leesburg Pike

Falls Church, VA, 22041-3803

SUBJ:  SIGNIFICANT DEVELOPMENT REPORT:  LITTLE YELLOW RIVER WATERSHED RESTORATION

Reference:  (a)  Notice of Award # F24AC02959-00

Dear Mr. Wurster,

- Reference (a) awarded a directed grant of $814,858 to the Wisconsin Waterfowl Association to undertake ditch disablements on lateral ditches that feed the Little Yellow River.   This letter reports a “significant development” and requests guidance.  It also describes our willingness to consider expansion of our restoration efforts in this general location if additional funds should be available.

- Status of contractor bids

  - Since the start of the project a month ago (as specified in reference (a)), WWA has mobilized its restoration team, developed and distributed bid proposals, met with interested contractors, and generated the needed contracts to undertake this project.

  - Three of seven initially interested contractors responded with wide ranging bids—from $525,000 to $13.3 million dollars for identical scopes of work originally estimated at $733,333 (see attachment (1) bid summary).   As a reminder, initial estimates of costs were jointly developed with USFWS project representatives.  It’s not clear what is driving this significant range of proposed bids.

  - WWA met with the low-bid contractor and after due diligence, we were prepared to provide a Notice to Proceed.  However prior to this notification, this low bid contractor withdrew their bid as of 14 November based on the owner’s emerging health problems.

- Insufficiency of funding for current scope of work

  - WWA is prepared to engage with the next lowest bid contractor to negotiate pricing and put them under contract.  Significantly, this contractor’s initial

SUBJ:  WWA Update on the Little Yellow River Watershed Restoration (cont’d)

pricing is $2,319,242. Consistent with our proposal, we can move forward with reducing proposal scope to the available funds, pending negotiations with the contractor.

  - REQUEST:  Please advise if there are additional funds to retain the same scope, so we may adjust our planning and negotiations accordingly.   While we will advise the next-lowest bid contractor that the door is still open to their participation, each day of delay jeopardizes the timeline of the project, and the availability of this contractor.

  - If more funds are available to sustain the project’s original scope of work, that level of funding will require WWA to undertake additional accounting activity to comply with 2 CFR Part 200, Subpart F.  Additional funds should be allocated to that effort that were not necessary or contemplated in the original WWA proposal.  Depending on USFWS guidance, WWA can provide an estimate of these costs.

- Willingness to undertake scope expansion

  - If there are additional funds to undertake additional, similar restoration work in this general location, WWA is willing to accept a modification to our existing agreement to collaboratively design those restorations, then administer and manage contractors to accomplish that work.

  - More complex project work such as subcontracting road- and stream-crossing designs, then contracting the construction work, and administering that work may be possible, depending on negotiated expectations.

  - Both a. and b. above would require a reconsideration of WWA costs and a renegotiation of project timelines.

- I look forward to hearing from you.

Warmly,

Bruce Ross

Executive Director

Copy: Mr. Brad Strobel

Attachment: Bid Summaries